## Gantt Chart Template
PROJECT TITLE
PROJECT MEMBERS & ROLES |  |  |  |  | Project Lead, Developer
Developer
TASK TITLE | START DATE | DUE DATE | DURATION (Days) | PCT OF TASK COMPLETE
[5 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
Intersession Week
Game3023 Coursework | [5 empty] | E1-A: Assets and Input E1-B: Project Plan Q1 | E2-A E2-B Q2 | E3-A E3-B Q3 | E4-A E4-B Q4 | E5-A E5-B Q5 | Midterm Assigned E6-A E6-B Q6 |  | Midterm Checkup | Midterm Due E7-A E7-B Q7 | E8-A E8-B Q8 | Q9 | Term Project Beta Release Q10 |  | Term Project Gold Release
Lab Exercise 1 | 2023-09-11 | 9-15-23 | 4 | 0% | bar: Week 1 to Week 2
Lab Exercise 2 | 9-14-23 | 9-18-23 | 4 | 0% | bar: Week 3
Lab Exercise 3 | 9-18-23 | 9-22-23 | 4 | 0% | bar: Week 4
Lab Exercise 4 | 9-23-23 | 9-27-23 | 4 | 0% | bar: Week 5
Lab Exercise 5 | 2010-01-23 | 2010-05-23 | 4 | 0% | bar: Week 6
Lab Exercise 6 | 2010-09-23 | 10-13-23 | 4 | 0% | bar: Week 7
Midterm | 2023-10-20 | 2023-11-17 | 27 | 0% | bar: Week 7 to Week 10
Lab Exercise 7 |  |  | 4 | 0% | bar: Week 10
Lab Exercise 8 |  |  | 4 | 0% | bar: Week 11
Quizzes | 2001-05-23 |  | -36503 | 0% | bar: Week 2 to Week 7; Week 9 to Week 13
Your Tasks (Recommended to include content outside Game3023, as it often affects planning)
Add partner and Joss to GH Repository with Unity Project uploaded | 2023-09-08 | 2023-09-15 | 7 | 0% | bar: Week 1 to Week 2
Pikeymans(TM) System allows one to select and use a Pikeyman which has unique stats and types |  |  | 0 | 0%
Pikeymans(TM) Battle sequence allows players to ask their Pikeyman to use Moves to defeat opposing Pikeyman) |  |  | 0 | 0%
Pikeymans(TM) Move System allows developers to create Moves which have unique stats, effects, and Types |  |  | 0 | 0%
Capture Pikeymans(TM) - Pikeymans encountered in the Wild may be captured by using a PikeyCube(TM) Capture Device |  |  | 0 | 0%
Pikeyman Trainer Battles (must battle multiple Pikeymans in a row to win) |  |  | 0 | 0%
Major Assignments/Exams in other courses... |  |  | 0 | 0%
etc. |  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%

## Try Smartsheet
Try Smartsheet for Free